## Gantchart
GANTT CHART SE Mini Project 1A | [6 empty] | Smartsheet Tip ➜ | [5 empty] | A Gantt chart's visual timeline allows you to see details about each task as well as project dependencies.
PROJECT TITLE | Fremedy Plus | [5 empty] | DEPARTMENT NAME : Department of Computer Scienece(Data Science)
PROJECT GUIDE | Richa | [5 empty] | DATE | [6 empty] | 2024-10-07
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION(Weeks) | PCT OF TASK COMPLETE | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[7 empty] | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F
1 | Project Conception and Initiation
1.1 | Project Orientation | A | 2024-07-08 | 2024-07-12 | 1 | 100% | bar: WEEK 1 M to WEEK 1 F
1.1 | Group Formation | A | 2024-07-08 | 2024-07-12 | 1 | 100% | bar: WEEK 1 M to WEEK 1 F
1.1 | Area of Problem Search | A | 2024-07-08 | 2024-07-12 | 1 | 100% | bar: WEEK 1 M to WEEK 1 F
1.2 | Project Title | A,B,C | 2024-07-15 | 2024-07-19 | 1 | 100% | bar: WEEK 2 M to WEEK 2 F
1.3 | Feasibility |  | 2024-07-15 | 2024-07-19 | 1 | 100% | bar: WEEK 2 M to WEEK 2 F
1.4 | Literature Review |  | 2024-07-22 | 2024-07-26 | 1 | 100% | bar: WEEK 3 M to WEEK 3 F
1.5 | Frame Objectives |  | 2024-07-22 | 2024-07-26 | 1 | 100% | bar: WEEK 3 M to WEEK 3 F
1.6 | Abstract | A | 2024-07-22 | 2024-07-26 | 1 | 100% | bar: WEEK 3 M to WEEK 3 F
1.7 | Scope | B | 2024-07-22 | 2024-07-26 | 1 | 100% | bar: WEEK 3 M to WEEK 3 F
1.8 | Propose Soution | A,B,C | 2024-07-22 | 2024-07-26 | 1 | 100% | bar: WEEK 3 M to WEEK 3 F
1.9 | Technology stack | B | 2024-07-22 | 2024-07-26 | 1 | 100% | bar: WEEK 3 M to WEEK 3 F
1.1 | Benefits / Advantages / Features |  | 2024-07-22 | 2024-07-26 | 1 | 100% | bar: WEEK 3 M to WEEK 3 F
1.11 | Technical Training |  | 2024-07-29 | 2024-08-09 | 2 | 100% | bar: WEEK 4 M to WEEK 4 F
1.12 | Timeline Finalization | B | 2024-07-29 | 2024-08-02 | 1 | 100% | bar: WEEK 4 M to WEEK 4 F
2 | Project Design
2.1 | Proposed System | A,B,C | 2024-08-05 | 2024-08-09 | 1 | 100% | bar: WEEK 5 M to WEEK 5 F
2.2 | Flow Diagram | A | 2024-08-12 | 2024-08-16 | 1 | 100% | bar: WEEK 6 M to WEEK 6 F
2.3 | Design(Flow Of Modules) | A | 2024-08-05 | 2024-08-23 | 3 | 100% | bar: WEEK 7 M to WEEK 7 F
3 | Project Implementation
3.1 | Module-1 | X | 2024-08-05 | 2024-08-16 | 2 | 100% | bar: WEEK 7 M to WEEK 7 F
3.2 | Module-2 | Y | 2024-08-19 | 2024-08-30 | 2 | 100% | bar: WEEK 8 M to WEEK 9 F
3.3 | Module-3 | Y | 2024-09-02 | 2024-09-13 | 2 | 100% | bar: WEEK 10 M to WEEK 10 F
3.4 | Module-4 | Z | 2024-09-17 | 2024-10-04 | 3 | 100% | bar: WEEK 10 M to WEEK 11 F
4 | Testing
4.1 | Design of Test Cases | A,B,C | 2024-10-07 | 2024-10-11 | 1 | 100% | bar: WEEK 12 M to WEEK 12 F
4.2 | Graphical Representation | A | 2024-10-07 | 2024-10-11 | 1 | 100% | bar: WEEK 12 M to WEEK 12 F
4.3 | Report Preparation | A | 2024-09-17 | 2024-10-04 | 1 | 100% | bar: WEEK 10 M to WEEK 11 F